## RRU
Task ID | Operation ID | Preceding Op | Skills Required | Num. Of Workers | Task Duration
1 | 1 |  | Electrical | 1 | 0.5
1 | 2 | 1 | Mechanical | 2 | 1
1 | 3 | 2 | Mechanical | 1 | 1
1 | 4 | 3 | Electrical | 1 | 0.5
2 | 1 |  | Mechanical | 2 | 2.5
2 | 2 | 1 | Mechanical | 1 | 0.7
2 | 3 | 1 | Mechanical | 1 | 0.7
2 | 4 | 1 | Mechanical | 1 | 0.7
2 | 5 | 1 | Mechanical | 1 | 0.7
2 | 6 | 1 | Mechanical | 1 | 0.7
2 | 7 | 1 | Mechanical | 1 | 0.7
2 | 8 | 1 | Mechanical | 1 | 0.7
2 | 9 | 1 | Mechanical | 1 | 0.7
2 | 10 | 1 | Mechanical | 1 | 0.7
2 | 11 | 1 | Mechanical | 1 | 0.7
2 | 12 | 2;3;4;5;6;7;8;9;10;11 | Mechanical | 2 | 2.5
3 | 1 |  | Electrical | 1 | 0.25
3 | 2 | 1 | Electrical | 2 | 0.5
3 | 3 | 2 | Automation | 1 | 0.5
3 | 4 | 3 | Electrical | 1 | 0.25
4 | 1 |  | Mechanical | 1 | 0.5
4 | 2 | 1 | Mechanical | 1 | 1.5
4 | 3 | 2 | Mechanical | 1 | 0.5
4 | 4 | 3 | Mechanical | 1 | 0.5
5 | 1 |  | Mechanical | 1 | 0.25
5 | 2 | 1 | Mechanical | 1 | 0.5
5 | 3 | 1 | Mechanical | 1 | 0.5
5 | 4 | 3 | Mechanical | 1 | 0.25
6 | 1 |  | Electrical | 1 | 0.2
6 | 2 | 1 | Mechanical | 2 | 0.3
6 | 3 | 1 | Lubrication | 1 | 0.7
6 | 4 | 2;3 | Mechanical | 2 | 0.3
6 | 5 | 4 | Electrical | 1 | 0.2

## HQL
Task ID | Operation ID | Preceding Op | Skills Required | Num. Of Workers | Task Duration
1 | 1 |  | Mechanical | 1 | 0.2
1 | 2 | 1 | Mechanical | 1 | 0.2
1 | 3 | 2 | Mechanical | 1 | 0.5
1 | 4 | 3 | Mechanical | 1 | 0.2
2 | 1 |  | Mechanical | 1 | 0.2
2 | 2 | 1 | Mechanical | 1 | 0.2
2 | 3 | 2 | Mechanical | 1 | 0.5
2 | 4 | 3 | Mechanical | 1 | 0.2
3 | 1 |  | Mechanical | 1 | 0.2
3 | 2 | 1 | Mechanical | 1 | 1
3 | 3 | 2 | Mechanical | 1 | 0.8
3 | 4 | 3 | Mechanical | 1 | 0.6
4 | 1 |  | Mechanical | 1 | 0.2
4 | 2 | 1 | Mechanical | 1 | 1
4 | 3 | 2 | Mechanical | 1 | 0.8
4 | 4 | 3 | Mechanical | 1 | 0.6
5 | 1 |  | Mechanical | 1 | 0.2
5 | 2 | 1 | Mechanical | 1 | 1
5 | 3 | 2 | Mechanical | 1 | 0.8
5 | 4 | 3 | Mechanical | 1 | 0.6
6 | 1 |  | Mechanical | 1 | 0.2
6 | 2 | 1 | Mechanical | 1 | 1
6 | 3 | 2 | Mechanical | 1 | 0.8
6 | 4 | 3 | Mechanical | 1 | 0.6
7 | 1 |  | Mechanical | 1 | 0.7
8 | 1 |  | Mechanical | 1 | 0.5
9 | 1 |  | Mechanical | 1 | 0.3
10 | 1 |  | Mechanical | 1 | 0.1
11 | 1 |  | Mechanical | 1 | 0.7
12 | 1 |  | Mechanical | 1 | 0.5
13 | 1 |  | Mechanical | 1 | 0.3
14 | 1 |  | Mechanical | 2 | 2.5
14 | 2 | 1 | Lubrication | 1 | 1.5
14 | 3 | 2 | Electrical | 1 | 0.7
14 | 4 | 3 | Mechanical | 2 | 2
15 | 1 |  | Mechanical | 2 | 2.5
15 | 2 | 1 | Lubrication | 1 | 1.5
15 | 3 | 2 | Electrical | 1 | 0.7
15 | 4 | 3 | Mechanical | 2 | 2
16 | 1 |  | Mechanical | 2 | 2.5
16 | 2 | 1 | Lubrication | 1 | 1.5
16 | 3 | 2 | Electrical | 1 | 0.7
16 | 4 | 3 | Mechanical | 2 | 2
17 | 1 |  | Mechanical | 2 | 2.5
17 | 2 | 1 | Lubrication | 1 | 1.5
17 | 3 | 2 | Electrical | 1 | 0.7
17 | 4 | 3 | Mechanical | 2 | 2
18 | 1 |  | Mechanical | 2 | 2.5
18 | 2 | 1 | Lubrication | 1 | 1.5
18 | 3 | 2 | Electrical | 1 | 0.7
18 | 4 | 3 | Mechanical | 2 | 2
19 | 1 |  | Mechanical | 2 | 2.5
19 | 2 | 1 | Lubrication | 1 | 1.5
19 | 3 | 2 | Electrical | 1 | 0.7
19 | 4 | 3 | Mechanical | 2 | 2
20 | 1 |  | Mechanical | 2 | 2.5
20 | 2 | 1 | Lubrication | 1 | 1.5
20 | 3 | 2 | Electrical | 1 | 0.7
20 | 4 | 3 | Mechanical | 2 | 2

## ITP
Task ID | Operation ID | Preceding Op | Skills Required | Num. Of Workers | Task Duration
1 | 1 |  | Mechanical | 1 | 0.1
1 | 2 | 1 | Mechanical | 1 | 0.3
1 | 3 | 2 | Mechanical | 1 | 0.7
1 | 4 | 3 | Mechanical | 1 | 0.1
2 | 1 |  | Mechanical | 2 | 2
2 | 2 | 1 | Mechanical | 2 | 0.6
2 | 3 | 2 | Electrical | 1 | 0.2
2 | 4 | 3 | Mechanical | 2 | 1.5
3 | 1 |  | Mechanical | 2 | 2.5
3 | 2 | 1 | Lubrication | 1 | 1.5
3 | 3 | 2 | Electrical | 1 | 0.7
3 | 4 | 3 | Mechanical | 2 | 2
4 | 5 |  | Mechanical | 2 | 1
4 | 6 | 1 | Lubrication | 1 | 2
4 | 7 | 2 | Electrical | 1 | 1.3
4 | 8 | 3 | Mechanical | 2 | 1.5
5 | 9 |  | Mechanical | 2 | 2.2
5 | 10 | 1 | Lubrication | 1 | 1.7
5 | 11 | 2 | Electrical | 1 | 0.5
5 | 12 | 3 | Mechanical | 2 | 1.2
6 | 1 |  | Mechanical | 2 | 2
7 | 1 |  | Mechanical | 2 | 0.7
8 | 1 |  | Mechanical | 2 | 0.7
9 | 1 |  | Mechanical | 2 | 0.7
10 | 1 |  | Mechanical | 2 | 1
11 | 1 |  | Mechanical | 2 | 1
12 | 1 |  | Mechanical | 2 | 0.7
13 | 1 |  | Mechanical | 2 | 0.7
14 | 1 |  | Mechanical | 2 | 1.2
15 | 1 |  | Mechanical | 2 | 1.2
16 | 1 |  | Mechanical | 2 | 1
17 | 1 |  | Mechanical | 1 | 2
18 | 1 |  | Mechanical | 1 | 0.5
19 | 1 |  | Mechanical | 1 | 0.5
20 | 1 |  | Mechanical | 1 | 0.5
21 | 1 |  | Mechanical | 1 | 0.5
22 | 1 |  | Mechanical | 1 | 0.5
23 | 1 |  | Mechanical | 1 | 0.5
24 | 1 |  | Mechanical | 1 | 0.5
25 | 1 |  | Mechanical | 1 | 0.5
26 | 1 |  | Mechanical | 1 | 0.5
27 | 1 |  | Mechanical | 1 | 0.5
28 | 1 |  | Mechanical | 1 | 0.2
28 | 2 | 1 | Mechanical | 1 | 0.7
28 | 3 | 2 | Mechanical | 1 | 0.1
28 | 4 | 3 | Mechanical | 1 | 0.2
29 | 1 |  | Automation | 1 | 0.2
29 | 2 |  | Automation | 1 | 0.2
29 | 3 |  | Automation | 1 | 0.2
29 | 4 |  | Automation | 1 | 0.2
30 | 1 |  | Automation | 1 | 0.3
31 | 1 |  | Automation | 1 | 0.3
32 | 1 |  | Automation | 1 | 0.3
33 | 1 |  | Automation | 1 | 0.3
34 | 1 |  | Mechanical | 1 | 0.7
35 | 1 |  | Mechanical | 1 | 0.5
36 | 1 |  | Mechanical | 1 | 0.3
37 | 1 |  | Mechanical | 1 | 0.1
38 | 1 |  | Mechanical | 1 | 0.7
39 | 1 |  | Mechanical | 1 | 0.5
40 | 1 |  | Mechanical | 1 | 0.3

## ISS
Task ID | Operation ID | Preceding Op | Skills Required | Num. Of Workers | Task Duration
1 | 1 |  | Calibration | 1 | 0.7
2 | 1 |  | Calibration | 1 | 0.7
3 | 1 |  | Calibration | 1 | 0.7
4 | 1 |  | Calibration | 1 | 0.7
5 | 1 |  | Calibration | 1 | 0.3
6 | 1 |  | Calibration | 1 | 0.3
7 | 1 |  | Calibration | 1 | 0.3
8 | 1 |  | Calibration | 1 | 1
9 | 1 |  | Calibration | 1 | 1
10 | 1 |  | Calibration | 1 | 1
11 | 1 |  | Calibration | 1 | 0.5
12 | 1 |  | Calibration | 1 | 0.2
13 | 1 |  | Mechanical | 2 | 1.5
13 | 2 | 1 | Electrical | 1 | 0.7
13 | 3 | 2 | Lubrication | 1 | 0.6
13 | 4 | 3 | Mechanical | 1 | 1.1
13 | 5 | 4 | Mechanical | 1 | 0.2
14 | 1 |  | Mechanical | 2 | 1.5
14 | 2 | 1 | Electrical | 1 | 0.7
14 | 3 | 2 | Lubrication | 1 | 0.6
14 | 4 | 3 | Mechanical | 1 | 1.1
14 | 5 | 4 | Mechanical | 1 | 0.2
15 | 1 |  | Mechanical | 2 | 1.5
15 | 2 | 1 | Electrical | 1 | 0.7
15 | 3 | 2 | Lubrication | 1 | 0.6
15 | 4 | 3 | Mechanical | 1 | 1.1
15 | 5 | 4 | Mechanical | 1 | 0.2
16 | 1 |  | Mechanical | 1 | 0.3
17 | 1 |  | Mechanical | 1 | 0.3
18 | 1 |  | Mechanical | 1 | 0.3
19 | 1 |  | Mechanical | 1 | 0.3
20 | 1 |  | Mechanical | 1 | 0.3
21 | 1 |  | Mechanical | 1 | 0.3
22 | 1 |  | Mechanical | 1 | 0.3
23 | 1 |  | Mechanical | 1 | 0.3
24 | 1 |  | Mechanical | 1 | 0.3
25 | 1 |  | Mechanical | 1 | 0.3
26 | 1 |  | Mechanical | 1 | 0.3
27 | 1 |  | Mechanical | 1 | 0.3
28 | 1 |  | Mechanical | 1 | 0.3
29 | 1 |  | Mechanical | 1 | 0.3
30 | 1 |  | Mechanical | 1 | 0.3
31 | 1 |  | Mechanical | 1 | 0.3
32 | 1 |  | Mechanical | 1 | 0.3
33 | 1 |  | Electrical | 1 | 0.1
33 | 2 | 1 | Calibration | 1 | 1
33 | 3 | 2 | Electrical | 1 | 0.3
33 | 4 | 3 | Electrical | 1 | 0.4
34 | 1 |  | Electrical | 1 | 0.1
34 | 2 | 1 | Calibration | 1 | 1
34 | 3 | 2 | Electrical | 1 | 0.3
34 | 4 | 3 | Electrical | 1 | 0.4
35 | 1 |  | Mechanical | 1 | 0.2
35 | 2 | 1 | Electrical | 1 | 0.7
35 | 3 | 2 | Mechanical | 1 | 0.1
35 | 4 | 3 | Mechanical | 1 | 0.2
36 | 1 |  | Mechanical | 2 | 1.5
36 | 2 | 1 | Mechanical | 1 | 1.2
36 | 3 | 1 | Mechanical | 1 | 0.9
36 | 4 | 2.3 | Mechanical | 2 | 1.1

## EMS
Task ID | Operation ID | Preceding Op | Skills Required | Num. Of Workers | Task Duration
1 | 1 |  | Mechanical | 1 | 0.2
1 | 2 | 1 | Calibration | 1 | 0.5
1 | 3 | 2 | Mechanical | 1 | 0.2
2 | 1 |  | Mechanical | 1 | 0.2
2 | 2 | 1 | Calibration | 1 | 0.5
2 | 3 | 2 | Mechanical | 1 | 0.2
3 | 1 |  | Mechanical | 2 | 0.2
3 | 2 | 1 | Calibration | 1 | 1.5
3 | 3 | 2 | Electrical | 1 | 1
3 | 4 | 3 | Mechanical | 2 | 0.5
4 | 1 |  | Mechanical | 2 | 0.2
4 | 2 | 1 | Calibration | 1 | 1.5
4 | 3 | 2 | Electrical | 1 | 1
4 | 4 | 3 | Mechanical | 2 | 0.5
5 | 1 |  | Mechanical | 2 | 0.2
5 | 2 | 1 | Calibration | 1 | 1.5
5 | 3 | 2 | Electrical | 1 | 1
5 | 4 | 3 | Mechanical | 2 | 0.5
6 | 1 |  | Mechanical | 2 | 0.2
6 | 2 | 1 | Calibration | 1 | 1.5
6 | 3 | 2 | Electrical | 1 | 1
6 | 4 | 3 | Mechanical | 2 | 0.5
7 | 1 |  | Mechanical | 2 | 0.2
7 | 2 | 1 | Calibration | 1 | 1.5
7 | 3 | 2 | Electrical | 1 | 1
7 | 4 | 3 | Mechanical | 2 | 0.5
8 | 1 |  | Mechanical | 2 | 0.2
8 | 2 | 1 | Calibration | 1 | 1.5
8 | 3 | 2 | Electrical | 1 | 1
8 | 4 | 3 | Mechanical | 2 | 0.5
9 | 1 |  | Mechanical | 2 | 0.2
9 | 2 | 1 | Calibration | 1 | 1.5
9 | 3 | 2 | Electrical | 1 | 1
9 | 4 | 3 | Mechanical | 2 | 0.5
10 | 1 |  | Mechanical | 1 | 0.6
11 | 1 |  | Mechanical | 1 | 0.6
12 | 1 |  | Mechanical | 1 | 0.6
13 | 1 |  | Mechanical | 1 | 0.6
14 | 1 |  | Mechanical | 1 | 0.6
15 | 1 |  | Mechanical | 1 | 0.6
16 | 1 |  | Mechanical | 1 | 0.6
17 | 1 |  | Mechanical | 1 | 0.2
17 | 2 | 1 | Electrical | 1 | 0.3
17 | 3 | 1 | Lubrication | 1 | 0.1
17 | 4 | 2;3 | Electrical | 1 | 0.3
17 | 5 | 4 | Mechanical | 1 | 0.2
18 | 1 |  | Mechanical | 1 | 0.2
18 | 2 | 1 | Electrical | 1 | 0.3
18 | 3 | 1 | Lubrication | 1 | 0.1
18 | 4 | 2;3 | Electrical | 1 | 0.3
18 | 5 | 4 | Mechanical | 1 | 0.2
19 | 1 |  | Mechanical | 2 | 0.2
19 | 2 | 1 | Electrical | 1 | 0.3
19 | 3 | 1 | Lubrication | 1 | 0.1
19 | 4 | 2;3 | Electrical | 1 | 0.3
19 | 5 | 4 | Mechanical | 2 | 0.2
20 | 1 |  | Mechanical | 2 | 0.2
20 | 2 | 1 | Electrical | 1 | 0.3
20 | 3 | 1 | Lubrication | 1 | 0.1
20 | 4 | 2;3 | Electrical | 1 | 0.3
20 | 5 | 4 | Mechanical | 2 | 0.2
21 | 1 |  | Mechanical | 1 | 0.2
21 | 2 | 1 | Electrical | 1 | 0.3
21 | 3 | 1 | Lubrication | 1 | 0.1
21 | 4 | 2;3 | Electrical | 1 | 0.3
21 | 5 | 4 | Mechanical | 1 | 0.2

## TLU
Task ID | Operation ID | Preceding Op | Skills Required | Num. Of Workers | Task Duration
1 | 1 |  | Mechanical | 2 | 0.5
1 | 2 | 1 | Lubrication | 1 | 1.5
1 | 3 | 1 | Lubrication | 1 | 0.5
1 | 4 | 2;3 | Mechanical | 2 | 0.3
2 | 1 |  | Electrical | 1 | 0.2
2 | 2 | 1 | Mechanical | 1 | 0.3
2 | 3 | 1 | Mechanical | 1 | 0.7
2 | 4 | 2;3 | Electrical | 1 | 0.2
3 | 1 |  | Electrical | 1 | 0.2
3 | 2 | 1 | Mechanical | 1 | 0.3
3 | 3 | 1 | Mechanical | 1 | 0.7
3 | 4 | 2;3 | Electrical | 1 | 0.2
4 | 1 |  | Electrical | 1 | 0.2
4 | 2 | 1 | Mechanical | 1 | 0.3
4 | 3 | 1 | Mechanical | 1 | 0.7
4 | 4 | 2;3 | Electrical | 1 | 0.2
5 | 1 |  | Mechanical | 2 | 0.5
5 | 2 | 1 | Mechanical | 1 | 0.1
5 | 3 |  | Mechanical | 1 | 0.1
5 | 4 | 2;3 | Mechanical | 2 | 0.5
6 | 1 |  | Mechanical | 2 | 0.5
6 | 2 | 1 | Lubrication | 1 | 0.1
6 | 3 | 1 | Lubrication | 1 | 0.5
6 | 4 | 2;3 | Mechanical | 2 | 0.5
7 | 1 |  | Mechanical | 1 | 0.3
7 | 2 | 1 | Electrical | 1 | 0.5
7 | 3 | 1 | Electrical | 1 | 0.5
7 | 4 | 2;3 | Mechanical | 1 | 0.7
8 | 1 |  | Mechanical | 1 | 0.2
8 | 2 | 1 | Electrical | 1 | 0.3
8 | 3 | 1 | Lubrication | 1 | 0.3
8 | 4 | 2;3 | Electrical | 1 | 0.3
8 | 5 | 4 | Mechanical | 1 | 0.2